## Worksheet Template
Worksheet 4.2
Staffing Plan
Instructions:Use the charts below to coordinate event staffing for the Go Human Activation. Add additional lines as needed for the number of shifts, teams, and event staff available. An example of a completed Staffing Plan for the Indio Go Human activation is available on the next tab. Notes: Shifts: Plan for multiple shifts if the total event time, including set-up and breakdown, exceeds 8 hours. For events with multiple shifts, identify the time period for each shift and the staff that will be completing those shifts. Teams:Organize the staff for each shift into different teams for different segments of the event (set-up, during, and breakdown). For the set-up, if staff is available, each Kit of Part activation element chosen is recommended to have a task leader and supporting staff. Staff could be a part of different teams, depending on the event segment. Bilingual Staff: Bilingual staff are helpful for events that are held in communities where languages other than English are frequently spoken. Use an * or other markers to identify bilingual staff.
Shifts
Shift 1: 11:00AM-10:30PM
Shift 2: 12:00PM-9:30PM
Shift 3: 12:00PM - 5:00PM
Shift 4: 5:00PM - 9:30PM
Teams | Set-Up (Description) |  | During Event (Description) |  | Breakdown (Description)
Team A:
Team B:
Team C:
Team D:
Team E:
Team F:
HH:MM AM-HH:MM PM | Pop-Up Set Up
Team A
HH:MM PM-HH:MM PM | Pop-Up Implementation |  |  | Logistics | CBOs | Vendors & Volunteers
| Team A: (Element #1) | Team B: (Element #2) | Team C: (Element #3) | Team D | Team E | Team F
HH:MM PM-HH:MM PM | Event Assignment
HH:MM PM-HH:MM PM | Breakdown
HH:MM PM-HH:MM PM | Final Breakdown
| Main Contacts | Phone Number
| Team #1 | [additional detail of tasks for the team]
| Team #2 | [additional detail of tasks for the team]
| Team #3 | [additional detail of tasks for the team]

## Indio Example
Worksheet Template 7.3
Staffing Plan
Instructions:Use the charts below to coordinate event staffing for the Go Human Activation. Add additional lines as needed for the number of shifts, teams, and event staff available. An example of a completed Staffing Plan for the Indio Go Human activation is available on the next tab. Notes: Shifts: Plan for multiple shifts if the total event time, including set-up and breakdown, exceeds 8 hours. For events with multiple shifts, identify the time period for each shift and the staff that will be completing those shifts. Teams:Organize the staff for each shift into different teams for different segments of the event (set-up, during, and breakdown). For the set-up, if staff is available, each Kit of Part activation element chosen is recommended to have a task leader and supporting staff. Staff could be a part of different teams, depending on the event segment. Bilingual Staff: Bilingual staff are helpful for events that are held in communities where languages other than English are frequently spoken. Use an * or other markers to identify bilingual staff.
Shifts
Shift 1: 11:00AM-10:30PM | Shift 1: Team staff | Volunteers: ~ 7 per shift
Shift 2: 12:00PM-9:30PM | Shift 2: Team staff
Shift 3: 12:00PM - 5:00PM | Shift 3: Team staff + volunteers
Shift 4: 5:00PM - 9:30PM | Shift 4: Team staff + volunteers
Teams | Set-Up |  | During Event |  | Breakdown
Team A: | Prep work and install bike lane and bulb-out |  | Staff the information booth |  | Tear down of pop-up elements and final cleanup
Team B: | Install the parklets |  | Engage participants with pop-up elements |  | Tear down of parklets
Team C: | Install the artistic crosswalk |  | Float around the event site to help where its needed |  | Tear down of the artistic crosswalk
Team D: | Set up information booth; see below for detail description |  | Survey collection |  | Tear down of information booth
Team E: | Set up artworks (Raice's mural, Desert Sands coloring sheets, and wayfinding signage) |  | Scavenger Hunt |  | Tear down of artworks
Team F: | Coordinate vendors and volunteers; see below for detail description |  |  |  | Coordinate with vendors and volunteers
11:00AM-12:00PM | Pop-Up Set Up
Team A
| Carlos* - Lead | Jenny*
| Raquel* | Alberto*
12:00 PM- 4:00 PM | Pop-Up Implementation |  |  | Logistics | CBOs | Vendors & Volunteers
| Team A: Bike Lane/ Bulb-out | Team B: Parklet (2) | Team C: Artistic Crosswalk | Team D | Team E | Team F
| Carlos* - Lead | Raquel* - Lead | Alberto* - Lead | Leslie - Lead | Jenny* - Lead | Michelle - Lead
| Volunteer 1 | Volunteer 1 | Volunteer 1 | Volunteer 1 | Volunteer 1 | Raices
| Volunteer 2 | Volunteer 2 |  |  | Volunteer 2
4:00 PM-8:00PM | Event Assignment
| Information booth: | Demonstrations: | Floaters: | Survey Collection: | Scavenger Hunt:
| Michelle | Jenny* | Carlos* | Alianza volunteers | Alianza volunteers
|  | Raquel* | Leslie
Alberto*
8:00PM - 9:30PM | Breakdown
| Carlos* - Lead | Raquel* - Lead | Alberto* - Lead | Leslie - Lead | Jenny* - Lead | Michelle - Lead
| Volunteer 1 | Volunteer 1 | Volunteer 1 | Volunteer 1 | Volunteer 1
| Volunteer 2 | Volunteer 2
9:30PM - 10:30PM | Final Breakdown
| Carlos* - Lead | Jenny* - Lead
| Raquel* | Alberto*
| Main Contacts | Phone Number
Carlos Velasquez
Jenny Yu
Michelle Lieberman
Leslie Scott
Alberto Saldago
Raquel Jimenez
| Team D | Responsibilities include setting up the event information booth, external affairs, and working with the videographer/photographer to document the event.
| Team E | Responsibilities include working with Raices to have the artwork installation completed, artistic crosswalks installed, colored artwork from Desert Sands Unified hanged, and wayfinding stencils on the ground.
| Team F | Responsibilities include coordinating with community vendors, survey implementation documentation, and working with Alianza to coordinate their volunteers and scavenger hunt.