## READ ME FIRST
Scope of Work Template Instructions
Sustainable Communities Program
Active Transportation and Safety
(1) | This workbook provides two scope of work templates: one for Communitywide/Area Plans (SOW Plans) and one for Quick-Build projects (SOW Quick-Builds). Update the template that matches your proposed project and delete the unused template.
(2) | Insert Project Name at the top of the worksheet.
(2) | Applicants may modify Tasks and Subtasks to align with the work of their project.
(3) | Once the Tasks and Subtasks are set, provide a description of the activities within each Subtask (column C) and identify deliverables (column D).
(4) | Once the scope of work is complete, use the TIMELINE tab to create a project timeline. Provide the project name at the top of the worksheet. Shade the cells to indicate the time when subtasks are active. You may use symbols to indicate key meetings, completion of deliverables, etc. Provide a legend of any symbols used.

## SOW Plans
Project Name
Scope of Work - Community/Area Wide Plan (Example)
Note: the example scope of work is based on the elements outlined in Appendix A of the ATP Cycle 7 Guidelines. Please review Appendix A, "Active Transportation Plan for Disadvantaged Communities Guidance for Plans"
Link to ATP Cycle 7 Guidelines
| Task | Description | Deliverables
Task 1: Project Management
1.1 | Project Team Meetings | Organize Monthly Project Development Team Meetings | XXX
1.2 | Invoicing and Reporting | Monthly Invoicing and Project Reporting | XXX
1.3 | Close-out Files | ZIP file or link to all project files, organized by Task and Sub-Task | XXX
Task 2: Existing Conditions
2.1 | Data Collection and Mapping | Gather data that addresses components from Appendix A of the 2025 Active Tranportation Program Guidelines and develop maps to illustrate key data/identify relationships. Identify list of data needs from key departments and/or other sources. | XXX
2.2 | Existing Conditions Report | Create a draft and final version of Existing Conditions Report. Explain why excluded components from Appendix A of the 2025 Active Transportation Guidelines are not applicable. | XXX
Task 3: Technical Advisory Committee
3.1 | Technical Advisory Committee | Convene a Technical Advisory Committee to keep relevant stakeholders informed of the project and gather feedback on project milestones. | XXX
Task 4: Community Engagement
4.1 | Community Advisory Committee | Convene a Community Advisory Committee comprised of key community stakeholders to share project updates, to serve as project ambassadors to share updates and publicize events, and to provide feedback on project milestones. | XXX
4.2 | Community Engagement Plan | Identify an approach to community engagement, including both in person and virtual tactics, such as canvassing, walk and bike audits, community workshops, e-newsletters, and social media. The strategy should identify key audiences, engagement goals, and desired outcomes. | XXX
4.3 | Community Engagement Implementation | Complete community engagement activities identified in strategy from Task 4.2 | XXX
4.4 | Go Human Kit of Parts Pop-Up | Utilize the Go Human Kit of Parts to create a pop up demonstration of safety/placemaking infrastructure and solicit community feedback. | XXX
Task 5: Project Development and Prioritization
5.1 | Project List and Mapping | Develop a list of infrastructure and non-infrastructure projects based on existing conditions analysis and community engagement. Prepare maps, as needed, to illustrate project locations and identify opportunities for coordination. | XXX
5.2 | Project Prioritization | Develop or utilize an existing project prioritization methodology to develop a list of XX projects to prioritize for funding and implementation. | XXX
5.3 | Conceptual Design | Develop PSR Equilavent designs for XX project corridors/areas with cost estimates to support near-term funding opportunities and implementation. | XXX
Task 6: Plan Development
6.1 | Draft Plan | Draft Community or Area Wide Plan. The plan should include the components identified in Appendix A of the 2025 Active Tranportation Program Guidelines, such as the existing conditions data, funding, implementation, and maintenance considerations. | XXX
6.2 | Final Plan | Final Adopted Community or Area Wide Plan. The final plan should include a resolution showing the adoption of the plan by the city, county, or district. If the plan was prepared by a county transportation commission, regional transportation planning agency, MPO, school district, or transit district, the plan should indicate the support via resolution of the city(s) or county(s) in which the proposed facilities would be located. | XXX
6.3 | Final Plan Presentation | Present completed Plan to City Council, community workshops, or other venues | XXX

## SOW Quick-Builds
Project Name
Scope of Work - Quick Build Projects (Example)
Note: the example scope of work is based on the elements outlined in Appendix D of the ATP Cycle 7 Guidelines. Please review Appendix D, "Guidance for the 2025 ATP Quick-Build Projects" to develop your project scope of work and Caltrans Quick-Build Project Supplemental Guidance to develop your project scope of work
Link to ATP Cycle 7 Guidelines
Link to Caltrans Quick-Build Project Supplemental Guidance
| Task | Description | Deliverables
Task 1: Project Management
1.1 | Project Team Meetings | Organize Monthly Project Development Team Meetings. | XXX
1.2 | Invoicing and Reporting | Monthly Invoicing and Project Reporting. | XXX
1.3 | Project Close Out Files | Document and organize project deliverables and deliver in a zipped file. | XXX
Task 2: Existing Conditions
2.1 | Data Collection and Baseline Assessment | Compile existing conditions data to understand existing conditions and inform project evaluation (before/after project comparison). Examples of metrics that can be evaluated include: vehicle speeds and volumes; adhere to traffic laws; average travel time and delay for all road users; mode shift; user perceptions of the level of traffic stress and safety; user perceptions of driver behavior; and/or number of collisions and injuries. | XXX
2.2 | Project Constraints | Review or collect right-of-way information and other project constraints through as-builts and observations. | XXX
2.3 | Existing Conditions Report | Create a draft and final Existing Conditions Report. | XXX
Task 3: Technical Advisory Committee
3.1 | Technical Advisory Committee | Convene a Technical Advisory Committee to keep relevant stakeholders informed of the project and gather feedback on project milestones. | XXX
Task 4: Community Engagement
4.1 | Community Advisory Committee | Convene a Community Advisory Committee comprised of key community stakeholders to share project updates, to serve as project ambassadors to share updates and publicize events, and to provide feedback on project milestones. | XXX
4.2 | Community Engagement Plan | Identify an approach to community engagement, including both in person and virtual tactics, such as canvassing, walk and bike audits, community workshops, e-newsletters, and social media. The strategy should identify key audiences, engagement goals, and desired outcomes. Engagement efforts should gather community feedback to inform project design and evaluation. Methods to gather feedback may include brief intercept survey in the project area, project workshops or hearings, brief questionnaires for project users, and/or social media campaigns that encourage public feedback. | XXX
4.3 | Community Engagement Implementation | Complete community engagement activities identified in strategy from Task 4.2. | XXX
4.4 | Go Human Kit of Parts Safety Pop-Up | Utilize the Go Human Kit of Parts to create a pop up demonstration of safety infrastructure and solicit community feedback. | XXX
Task 5: Project Plans and Materials
5.1 | Quick Build Design Plans | Develop conceptual plans and PS&E package reviewed and signed by a licensed Professional Engineer. | XXX
5.2 | Implementation Plan | Develop an implementation plan that identifies the necessary materials (type and quantity), permits, traffic management plan, and/or implementation staff to implement the quick build design. The materials estimate should include the types and quantities needed to facilitate modifications to the quick build design. | XXX
Task 6: Implementation
6.1 | Project Implementation | Implement the quick build project through a contractor or local staff. | XXX
Task 7: Evaluation
7.1 | Data Collection | Collect post-installation data (at least 6 months post-installation) to inform project evaluation. The data collected should correspond to the existing conditions data. Examples of metrics that can be evaluated include: vehicle speeds and volumes; adhere to traffic laws; average travel time and delay for all road users; mode shift; user perceptions of the level of traffic stress and safety; user perceptions of driver behavior; and/or number of collisions and injuries. | XXX
7.2 | Evaluation Report | Create a draft and final Evaluation Report that evaluates the quick build project using the before/after data collected in tasks 2.1 and 7.1 and community feedback in task 4.3. | XXX
Task 8: Final Reports and Presentations
8.1 | Draft Final Report | Draft a final report that summarizes the project, including goals, engagement, and design process, and provides recommendations and next steps. | XXX
8.2 | Final Report | Finalize report based on comments from stakeholders, such as community advisory committee, technical advisory committee, etc. | XXX
8.3 | Presentations | Provide presentations to City Council, Commissions, etc. | XXX

## TIMELINE
PROJECT TIMELINE
| Project Title | YOUR PROJECT NAME HERE
Task Number | Task Title | Months after NTP (add columns if more months are needed)
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
1
1.1
1.2
1.3
2
2.1
2.2
2.3
2.4
2.5
2.6
3
3.1
3.2
3.3
3.4
3.5
3.6
4
4.1
4.2
4.3
4.4
4.5
4.6
5
5.1
5.2
5.3
4.4
4.5
4.6
6
6.1
6.2
6.3
6.4
6.5
6.6